## DEFINING YOUR PROJECT – 6 IMPORTANT CONSIDERATIONS!

Defining your project is all about ‘scope management’. Scope management is the process by which the deliverables and work to produce them are identified and defined. Identification and definition of the scope must describe what the project will include and what it will not include, i.e. what is in and out of scope. APM’S BODY OF KNOWLEDGE

The scope of the project is comprised of what has to be delivered (the project deliverables) and what work has to be done to deliver the project deliverables. Scope management should be continually addressed throughout the life of the project and includes regular monitoring and controlling.

The high level scope of the project should have been defined and documented in the business case. The depth and detail of the scope will develop as the project progresses and will be a breakdown of the original scope held in the Project Management Plan.

The scope can be broken down and refined by using a variety of break down structures:

• Product breakdown structure (PBS)

• Work breakdown structure (WBS)

• Organisational breakdown structure (OBS)

• Cost breakdown structure (CBS)

• Responsibility assignment matrix (RAM)

(Click on each of the above, for a definition and example)

So here are 6 Important things to consider when defining your project:

1. Stakeholder agreement – It is important to agree what is not in scope of the project, as to what is. Defining the project scope sounds obvious in principle. However, it is easy for assumptions to be made by various stakeholders on what is included in the scope. The easiest way to avoid this is to ask the project stakeholders to literally sign the WBS (or PBS). Being asked to sign their agreement against the scope will force a careful analysis of the requirement which can save a lot of time and cost later.

2. Don’t jump to the planning stage too soon – without a clear knowledge of the scope, planning will be ineffective. It is tempting to make assumptions and jump too early into the planning stage, rather than painstakingly agree the detailed scope of the work. Shortcutting will only lead to more problems later.

3. Involve all those who know the work – The development of work and product breakdown structures gives the project team an opportunity to engage with anyone who knows the work better than they may do. Those who have previously been involved in similar projects will readily spot missing elements of scope using their experience. This stage is also an opportunity to engage the wider project team in working together – effectively team building but at the same time creating a common vision of the work involved.

4. Ignoring time – creating a work breakdown structure allows the project team to define the work or products in a logical way, without being distracted by the timeline which comes later in the planning stage. By ensuring each step of defining and planning your project is done methodically, it will lead to a better result, and increase the chances of project success.

5. Pre-planning benefits – Developing the responsibility assignment matrix (RAM) before the planning stage allows the project team to avoid the distraction of reality at too early a stage. It is too tempting to modify resource requirement because of assumptions about availability instead of simply and methodically agreeing who should have responsibility for what work. It is also important to keep the distinction between responsibility (at this stage) and resource allocation (who will do the work – agreed at the planning stage).

6. Programmes and projects – There is often much confusion between programmes and projects, and even the job titles of project manager, programme manager, project director and programme director. It should be clear at this stage. Project management is like juggling three balls: time, cost and quality. Programme management is like a troupe of circus performers standing in a circle, each juggling three balls and swapping from time to time.( Source Geoff Reiss)

Source: http://2020projectmanagement.com/2013/10/6-important-considerations-when-defining-your-project/

## THE PRODUCT BREAKDOWN STRUCTURE (PBS)

The Product Breakdown Structure (PBS) identifies and defines all the products (deliverables) that the project has to produce. The product breakdown structure will show the scope broken down in a hierarchical manner and at its lowest level each product (deliverable) will be identified. It is an effective tool that details the physical components of a particular product or system under consideration. The structure serves to reduce a complex project, or product into manageable components. As a result, teams can obtain a clear understanding of a product, its components and what is required to provide those components.

EXAMPLE OF A PRODUCT BREAKDOWN STRUCTURE (PBS)

Although the PBS is created at the primary stages of a project, it is important that it is reviewed and revised at each stage of the project. The PBS can then be adjusted accordingly. When creating a PBS use the following guidelines:

- The top level represents the final product/project

- Sub-deliverables contain sub components of the final product

- Identify product components through group collaboration

- Product descriptions can be a useful component of the PBS

## THE WORK BREAKDOWN STRUCTURE (WBS)

The work breakdown structure (WBS) defines the work that is required in order to produce the product or deliverables. It is represented as a hierarchical subdivision of a project into work areas with the lowest generally being a work package or sometimes even an activity. The lowest level of the WBS should be consistent and agreed at the outset of the creation of the WBS. The WBS provides the foundation for all project management work, including planning, cost and effort estimation, resource allocation, and scheduling.
Creating a WBS:

- enables the definition of the total scope of work

- provides the ability to assign work to people responsible for carrying out the work

- establishes a control baseline

- measures accomplishments objectively when the work is done

- defines, collects and reports information at the appropriate level required

- defines the relationships between work, organisation and cost.

## THE ORGANISATIONAL BREAKDOWN STRUCTURE (OBS)

Project organisations can be broken down in much the same way as the work or product can. The OBS is created to reflect the strategy for managing the various aspects of the project and shows the hierarchical breakdown of the management structure.

## THE COST BREAKDOWN STRUCTURE (CBS)

Costs are allocated to the lowest level of the WBS. The tasks at this level can often be subdivided into discrete activities to be completed by different departments therefore one task may have several costs elements. Once costs have been assigned to tasks, it is possible to monitor the project in terms of actual, forecast and earned cost on a task.

In order to be able to summarise costs within projects across projects a CBS needs to be developed. The majority of organisations have a standard CBS that is applied across all projects and is nearly always determined by the finance department. Finance often refers to the structure as the code of accounts which includes other elements over and above pure costs. With some computerised tools, a separate CBS is set up which is normally a simplified version of the code of accounts so that it can be understood more easily by non-financial managers.

The overall purpose of the CBS is to breakdown all the associated costs for purposes of identification and control.

## THE RESPONSIBILITY ASSIGNMENT MATRIX (RAM)

Projects can involve large numbers of people often from different departments, functions and divisions of the business. The project manager is accountable for the project but this does not mean they are solely responsible for all the work involved. A Responsibility Matrix is used to define who in the organisation is responsible for individual work elements and deliverables. By forming a matrix  with the work breakdown structure and the organisational breakdown structure, responsibilities can be assigned to lower level tasks. Each task is assigned a WBS and OBS code, the department responsible, the person responsible, and the scope of work required.

R – Responsible

A – Accountable

C – Consult

I – Inform