PMS – Process Description

Issue Management

# Definitions

An Issue is:

Any point of contention, technical problem or bug, unexpected event, unassigned responsibility, client concern, a quality shortfall or gap, a potential schedule delay or improvement, a potential cost overrun or under run, a staffing problem, a risk event that has happened, an opportunity to streamline, etc. that might occur during the course of a project.   In short anything that could enhance project progress if followed-up or hamper it if not dealt with.

An Issue is always happening in the present.   It’s a current event, unlike a Risk which is something that might happen in the future or a Change that is a record of something that happened in the past.

An issue can be identified by the client, the steering committee or sponsor, the project manager, any team member or any stakeholder.

An Issue is not:

- An Action item, activity or task

- A risk (something that might happen)

- An opportunity to ‘point fingers’ or ‘brag’

Issue Management is:

A process to ensure that all issues are identified, documented and dealt with in a timely fashion and with minimum impact to the project. The issue management system is designed to provide a mechanism for tracking and controlling issues. This management system should cover:

- the identification and capture of each issue

- the appointment of an action manager to be responsible for getting each issue resolved by a specified date

- the logging and reporting of all outstanding issues

# Objectives

The objective of the Issue Management Process is to ensure that Managers at all levels understand:

- what an issue is

- that issues are to be expected in every project

- that issue management cannot be avoided or delegated

- that time will be needed, at short notice, to handle issues

- that having the ability to identify and deal with issues promptly and efficiently is the project managers most powerful tool through the project

# Outline of Procedure

- Identify and log each issue

- Identify a responsibility and escalation path for each

- Analyze each (preferable using a minimum of 3 alternative possible solutions)

- log analysis completed and actions taken

- Record and inform of the resolution

- Track and manage outstanding issues

- Keep issues visible at all times

# Issue Management Procedure

Scope

Any situation that will have an impact on the project objectives or schedule must be processed by an Issue Management procedure based on the following authorities, responsibilities, process and forms:

Authorities

| Activity | Authority |
| --- | --- |
| Raising an issue | Any project member or stakeholder |
| Acknowledging the issue | Project Manager |
| Assigning Action Manager ownership | Project Manager |
| Monitoring/Analyzing the issue | Action Manager |
| Recommending the issue resolution | Action Manager |
| Reviewing and updating the project issue log | Project Manager/Project Support Office |
| Reporting to senior management | Project Manager |

NOTE: For Larger, more complex projects, the detail behind these responsibilities should be documented in the Project Organization, Roles & responsibilities section of the Project Execution Plan (PEP) - .

To Manage an Individual Issue

| Responsibility | Action |
| --- | --- |
| Any project member or stakeholder | The situation is recognized as an issue and described on an issue form/database (in Part A - Issue Description/Details). |
| Project Support Office | The issue is logged on the issue management system and given the next issue number. Copies of the issue are sent to each sub-project leader for information. |
| Project Manager | The Project Manager assigns the Issue to an Action Manager for resolution. |
| Action Manager | Planned actions and/or analyses and their Outcomes are logged on the Action Log section of the form (Part B). |
| Action Manager | After ensuring all options have been properly identified and assessed, the Action Manager recommends a solution by updating Part C of the form accordingly |
| Project Manager | The issue is accepted as resolved and closed. (The Project Steering Committee/Sponsor and/or affected Stakeholder(s) should also approve resolutions with significant cost, schedule or scope implications). |
| Project Support Office or Project Manager | The decisions taken to resolve the issue are communicated to all necessary parties. |
| Project Manager | Project definition and plans are updated (and/or a Change Request raised) to reflect any changes introduced by the resolution of the issue and all contractual obligations are also followed. |

Detailed Responsibilities

Project Manager's responsibility

| Frequency | Action |
| --- | --- |
| At project meetings | Review all open issues with sub-project leaders and Issue Action Managers. |
| Monthly | Report to the project sponsor the total impact of all outstanding issues and impact to the overall project plans and schedule. |
| As required | Ensure all resolutions are implemented (including raising change requests where applicable) |

Project Support Office responsibilities

| Frequency | Action |
| --- | --- |
| Continually | Maintain the file of Issue forms and Action Logs within the Project Control Book. |
| Weekly | Check all open Issues and chase Action managers |
| For project meetings | Prepare current status of open issues. |
| As required | Circulate new issues and action details for information. Circulate issue log with closed and open issues listed. |

Forms

The Issue Form and Issue Log are shown on the next pages

|  | Issue Form | ISS# |  |
| --- | --- | --- | --- |
|  |  | ProjID |  |
|  | Project: |  |

| General Information |
| --- |
| Project Description |  | Proj Class |  |
| Sponsor: |  | Consultant: |  |
| Proj. Mngr: |  | Contractor: |  |
| Prep. by: |  | Date Prep: |  |

| Part A - Issue Description/Details |
| --- |
| Issue Title: |  | Date Raised: |  |
| Description of Issue: |  |
| Impact if not managed (include cost, schedule and scope/qual. impacts): |  |
| Priority: (L=1, M=3, H=5) |  | Impact: (L=1, M=3, H=5) |  | Severity Index: (Pri. x Imp.) |  |
| Issue Action Manager |  | Target Resolution Date |  |

| Part B - Issue Action Log |
| --- |
| Date | Action/Analysis Description | By | Outcome/Next Steps |

| Part C - Issue Resolution / Recommendation |
| --- |
| Recommendation / Resolution: |  |
| Cost Impact: |  | Schedule Impact: |  |
| Scope/Quality Impact: |  |

| Approvals |
| --- |
| Name: |  | Signature: |
| Title: | Project Manager |  |
| Date: |  |  |
| Name: |  | Signature: |
| Title: |  |  |
| Date: |  |  |