## User Guide
Reference: PMO-F-003, Rev: 0 Date of Impl: 15-Dec-09
This User Guide provides a step-by-step approach for using this [MWH Project Classification Utility Tool] in order to determine whether an idea is just 'business-as-usual' or a 'project', and in which case, it's Classification. This tool can be used to classify up to 24 such projects and must be used in conjunction with the MWH Project Classification Matrix and supporting guidelines for Construction, Service & Maintenance and Business Improvement Projects.
1 | The first step is to confirm that the idea or submission is really a project. For an initiative or idea to be considered a Project, you have to be able to answer Yes to all of the following 4 questions: 1) Duration: does it have clearly identifiable start and end points? 2) Uniqueness: does it create something new or unique? 3) Progressive elaboration: can it be broken down into tasks? 4) Well-defined goals: does it have clear objectives? If this is indeed a project then use the remaining steps below to further Classify it as an A, B or C Type project. NOTE: That the MoW has also chosen to include some TCO programs as projects but by being defined as a TCO program, no further classification is required
2 | In the [MWH Project List] worksheet: Enter the project name, category and type for each project being evaluated
3 | Use the [Size} worksheet to determine a size score for the project. Review the definition of each criterion in the worksheet by placing the cursor over the criterion title at the top of each column. Using the guidelines in the lower section of the worksheet, enter the appropriate score for each project in the relevant columns in the upper section of the sheet. Note that Construction projects have different scores than Business Improvement & Service & Maintenance ones.
4 | Use the [Complexity] worksheet to determine the complexity score for each project. Review the definition of each criterion in the worksheet by placing the cursor over the criterion title at the top of each column. Using the guidelines in the lower section of the worksheet, enter the appropriate score for each project in the relevant columns in the upper section of the worksheet.
5 | The tool will automatically calculate the total Size and Complexity Scores and the project Ratings in the [Classification Results] worksheet
6 | View the [Classification Map] worksheet for a pictorial view of where each project placed and whether they are an A, B or C Type.
7 | Apply the guidelines provided in the MWH Classification Matrix to determine the requirements for each project class

## MWH Project List
Reference: PMO-F-003, Rev: 0.0 Date of Impl: 15-Dec-09
Description | CATEGORY | TYPE
PROJECT CATEGORIES
|  |  | Strategic Initiatives (e.g. New service development, application/system implementations, Major Enhancements) | SI
|  |  | Regulatory - Mandatory/Imposed Initiatives (e.g. projects to deal with legal and/or regulatory requirements) | M
|  |  | Capital Projects - (e.g. infrastructural projects) | CP
|  |  | Operational - (e.g. software upgrades, maintenance) | OP
|  |  | Not Applicable | NA
PROJECT TYPES
|  |  | Construction | C
|  |  | Service & Maintenance | SM
|  |  | Business Improvement | BI

## Size
Reference: PMO-F-003, Rev: 0.0 Date of Impl: 15-Dec-09
Project Name | Total Project Budget | MWH Project Team | Project Duration | Total Size Rating | Size Rating
Construction Projects
[6 empty] | Budget | > BD20m | 30
|  |  |  | 0 |  |  | > BD10m and < BD20m | 20
|  |  |  | 0 |  |  | > BD5m and < BD10m | 12
|  |  |  | 0 |  |  | > BD500,000 and < BD5m | 8
|  |  |  | 0 |  |  | < BD 500,000 | 6
|  |  |  | 0 |  | Team Size | > 25 | 15
|  |  |  | 0 |  |  | > 10 and < 25 | 9
|  |  |  | 0 |  |  | > 5 and <10 | 6
|  |  |  | 0 |  |  | < 5 | 3
|  |  |  | 0 |  | Duration | > 36 months | 20
|  |  |  | 0 |  |  | > 24 and < 36 months | 15
|  |  |  | 0 |  |  | > 12 and < 24 months | 9
|  |  |  | 0 |  |  | < 12 months | 6
0
|  |  |  | 0 |  |  | BI & SM projects
|  |  |  | 0 |  | Budget | > BD500,000 | 30
|  |  |  | 0 |  |  | > BD100,000 and < BD500,000 | 20
|  |  |  | 0 |  |  | > BD10,000 and < BD100,000 | 12
|  |  |  | 0 |  |  | <BD10,000 | 6
|  |  |  | 0 |  | Team Size | > 15 | 15
|  |  |  | 0 |  |  | > 5 and < 15 | 9
|  |  |  | 0 |  |  | < 5 | 3
|  |  |  | 0 |  | Duration | > 12 months | 15
|  |  |  | 0 |  |  | > 6 and < 12 months | 9
|  |  |  | 0 |  |  | < 6 months | 3

## Complexity
Reference: PMO-F-003, Rev: 0.0 Date of Impl: 15-Dec-09
Project | Strategic Significance |  | # of Business Units ("Areas") within MoW Involved |  | Total # of Key Project Personnel Involved Ext. & Int. |  | Scarcity of Key Resources |  | Technical Complexity |  | Technology |  | Cross-Project Inter-Dependencies |  | # of locations involved in deployment |  | Stakeholder Involvement |  | Uniqueness |  | Total Complexity Scores
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Broad national, community, ministry or enterprise-wide impact. Large number of processes affected or results visible to constituents. Direct impact on MoW strategies. | 5 | >5 | 5 | >50 | 5 | Required resource(s) very scarce within MoW | 5 | Sate-of-the-art engineering novel. New methods/ techniques. Require extensive learning & research. | 5 | Involves new technology, innovations & integration | 5 | >2 Projects | 5 | > 6 | 5 | Multi-partner highly-involved stakeholders | 5 | Very Unique - Never been done before within MoW | 5
| Moderate significance (e.g. some Directorates, impact, few processes affected, minor public visibility). Relates to low or medium priority MoW strategies or objectives. | 3 | 3 to 5 | 3 | >11 <50 | 3 | Limited within MoW | 3 | Somewhat new engineering methods/techniques that require some research | 3 | Involves major changes to existing technology | 3 | 2 Projects | 3 | 3 - 5 | 3 | Ministry/enterprise-wide initiative, with less involved stakeholders | 3 | Have done this 1 - 2 times before OR some specific aspects have never been done before within MoW | 3
| Low significance (restricted to directorate or department, single process affected. Indirect or low impact on MoW strategies. | 1 | <3 | 1 | <10 | 1 | No Scarcity | 1 | Engineering methods/techniques already known and used | 1 | Involves existing technology | 1 | 1 Project | 1 | < 2 | 1 | Small team, limited number of partners or few stakeholders. | 1 | Have done this 3 or more times before with MoW | 1
Note on R2: Husam Sha'ath: Stakeholders are those entities (organizations or individuals) who either contribute to or are affected by the project.
Note on P2: Total number of sites, that also include consultant bases, which may be outside the country.
Note on F2: Key project personnel in all organizations, including, MOWH, Consultants, Contractors, etc. involved in the production of deliverables.
Note on H2: Resources include human, financial, and capital resources.
Note on J2: This is the engineering, or non-IT complexity of the project.
Note on L2: Refers to IT-systems involved in the project.
Note on D2: Business units are areas internal to the MWH, such as Directorates, etc. It does not include Contractors', Consultants', or any other stakeholder organizations or business areas.
Note on N2: Refer to the number of projects that have interdependencies with the current project.
Note on B2: Husam Sha'ath: The Strategic Significance covers the significance to the Kingdom, or to the MWH.

## Classification Results
Reference: PMO-F-003, Rev: 0.0 Date of Impl: 15-Dec-09
Name | Total Scores |  | Rating
| Size | Complexity | Size | Complexity | Overall

## Classification Map
Reference: PMO-F-003, Rev: 0.0 Date of Impl: 15-Dec-09
A
B
C