PMS Process Description

Risk Management

# Definitions:

A Risk is:

An uncertain or potential future event or condition that, if it occurs, will have a positive or negative effect on a project’s objectives.

A Risk is not:

- An Issue (i.e. has already happened).

- A Constraint or Assumption.

- An unexpected construction condition that is already covered by the project’s Reserve or Contingency funds policy.

Project Risk Event

A discrete occurrence of a Project Risk that has impacted the project for better or worse.

Project Risk Management

The systematic process of identifying, analyzing, and responding to project risks, either in the present or through developing contingency plans that can be quickly implemented if the risk event occurs.

Risk Probability:

An estimate of the likelihood that a given risk event will occur.

NOTE:  if the probability of a risk event is 100 %, it is no longer uncertain and is no longer a risk event.  It is now an issue or a constraint.

Risk Impact:

An estimate of the gain or loss that will be incurred if a risk event occurs, also called consequences or results.

Risk Severity:

A numerical scoring of a risk (obtained by multiplying the risk probability and the risk impact together).

Risk Response:

An action that can be taken for each identified Risk.

There are 5 possible Responses to a risk as follows:

- Acceptance:  Accept the risk and do nothing.

- Transference:  Share the project risk.  This does not reduce the probability of a risk event occurring; it only reduces the impact if it does (e.g. just like an insurance policy).

- Avoidance:  Change the project plan and / or project objectives to eliminate the risk or reduce the impact of the risk.

- Take Mitigation/Preventive Action:  Take some immediate action to reduce the probability and / or the impact of a risk event to below an acceptable threshold.   This will usually add to the project scope and increase the project budget/schedule.

- Contingency Planning:  Develop a detailed action plan that can be quickly enacted should the risk event occur.

# Objectives

The objectives of the risk management process are:

- To identify and document all project risks including their source/cause, probability and impact or consequences.

- To qualify and quantify each risk and so allow each risk to be understood and managed accordingly.

- To ensure each risk is properly assessed by key project players.

- To ensure the ongoing identification, assessment and reporting on risks.

# Outline of Procedure

- All risks should be identified early in the project (i.e. documented in the Project Charter).

- These should be further expanded upon as one of the first key steps when the core project team is assembled.   The “Risk Register” should be created very early in the planning phase (and used during that planning).

- Each risk should be quantified and assigned to a Risk Action Manager or “Risk Owner”.

- Each Risk should have one of 5 key actions assigned to it (and these actions should be put in place or implemented right away).

- All risks are logged to provide visibility and status information on an ongoing basis.

# Risk Management Procedure

The Risk Management process is detailed below:

Scope

All Risks must be identified and processed by the risk management procedure.

Authorities

| Activity | Authority |
| --- | --- |
| Identifying Risks | Any project member or stakeholder |
| Accepting risk as valid | Project Manager |
| Assessing impact of risks | Project Manager or designated Risk Owner |
| Accepting or rejecting a Risk Action | Project Manager |
| Implementing Risk Actions | Project Manager |

NOTE: The responsibilities and authorities for acceptance or rejection of various sized risks should be highlighted in the definition of the management structure.

To manage an individual risk

| Responsibility | Action |
| --- | --- |
| Project Manager | Assembles the Core Project team and conducts a Risk Analyses. This should be done as early as possible within the Planning Phase. |
| Risk Analysis Team | Risk Analysis Team Members should describe and quantify each Risk by completing “Part A – Risk Description” on a Risk Form. These details should include high level details of what could cause the risk to happen (Triggers) and the impact if it does (Consequences). |
| Risk Analysis Team | Assign a Probability Score (High = 5, Med = 3, Low =1) and an Impact Score (High =5, Med = 3, Low =1) to each risk and then multiply the 2 together to get a Risk Severity Score (e.g. valid Severity scores will be 1, 3, 5, 9,15 or 25). |
| Project Manager | Accepts the risk and risk severity score as valid, assigns a Risk Owner (or Risk Action Manager) and gives a target date for the completion of a further evaluation of the risk and recommended action. |
| Project Support | Logs the Risk into the Risk Management system and gives it the next Risk number. The original form and attachments are filed in the Project Control Book. Copies of the Risk Form are sent to and/or the Risk Owner and/or each sub-project leader for information as appropriate. |
| Risk Owner | Complete “Part B – Risk Analysis” of the Risk Form to document any subsequent analysis of the risk. Assessments are returned to the project support. |
| Risk Owner | Complete “Part C – Recommendation” of the Risk Form to document the recommended action to take regarding the risk. |
| Note: An agreed approach should be established on how to process Preventive and Contingency Planning activities. A possibility is to raise an Issue for each such that progress can be tracked and impacts properly quantified using the Issue Management Process. |
| Project Manager | Accepts the assessment details and recommendation by completing the bottom of the Risk Form. If the impact and/or the Severity Score is large, the Project Manager should also obtain the Sponsor’s and other Stakeholder’s acknowledgment and approval of the risk action. |
| Project Support | Updates the Risk register and records all Risk Forms/Actions in the Project Control Book. Provides regular reports and updates on Risks and schedules risk reviews as appropriate throughout the life of the project. Ensures Issues (and potentially Change Requests) are raised as appropriate to ensure and visibility and ongoing monitoring of all Preventive and Contingency Planning activities. |

To Run the Change Management System

Project Manager's responsibilities

| Frequency | Action |
| --- | --- |
| At project meetings | Review all outstanding risks with sub-project leaders. |
| Monthly | Report to the project Sponsor the total impact of all risks and to the overall project plans and time scales. |

Project Support responsibilities

| Frequency | Action |
| --- | --- |
| Continually | Maintain the file of all risks and up-to-date Risk Register in the Project Control Book/Data Base. |
| Weekly | Check all outstanding Risk Forms (those being assessed) to ensure evaluations are taking place and assessments being returned to the project office. |
| For project meetings | Prepare report with status of each outstanding Risk. |
| As required | Circulate new Risks for assessment. Collect risk Assessments and Action Recommendations from sub-project leaders or Risk Owners. Assemble all Risk Forms for project manager to approve actions. Circulate updated Risk register to project team members/Stakeholders as appropriate. |

Risk Templates

The following are the templates that must be used to manage Risks within all Ministry projects.

|  | Risk Form | RSK# |  |
| --- | --- | --- | --- |
|  |  | ProjID |  |
|  | Project: |  |

| General Information |
| --- |
| Project Description |  | Proj Class |  |
| Sponsor: |  | Consultant: |  |
| Proj. Mngr: |  | Contractor: |  |
| Prep. by: |  | Date Prep: |  |

| Part A - Risk Description |
| --- |
| Risk Title: |  | Date Raised: |  |
| Risk Description: |  |
| Probability: (L=1, M=3, H=5) |  | Impact: (L=1, M=3, H=5) |  | Severity Index: (Prob. x Imp.) |  |
| Event(s) that could cause Risk to happen (Triggers): |  |
| Impact if Risk happens (Consequences) |  |
| Risk Action Manager |  | Target Evaluation Date |  |

| Part B - Risk Analysis |
| --- |
| Date | Action/Analysis Description | By | Outcome/Next Steps |

| Part C - Recommendation |
| --- |
| Action: | Accept (Severity < 4) Transfer Avoid | Take Preventive Actions (> 6) Contingency Plan ( >10) |
| Details: |  |

| Approvals |
| --- |
| Name: |  | Signature: |
| Title: | Project Manager |  |
| Date: |  |  |
| Name: |  | Signature: |
| Title: |  |  |
| Date: |  |  |